## Slide 1
DEFINE MEASURE ANALYZE IMPROVE CONTROL
Jun 18-24 → Jun 25-Jul 8 → Jul 9-22 → Jul 23-Aug 5 → Aug 6-12
Primary Metric:
On-Time Arrival Rate (%) — flight on-time if arrives
within 15 minutes of scheduled arrival
Framework: DMAIC (Lean Six Sigma Green Belt)
Database: SQL — SQLite / DB Browser
Visualize: Tableau Public
Dashboard: Microsoft Power BI
DMAIC PROJECT CHARTER
Flight Delay Root Cause Analysis | US Domestic Flights 2023
US domestic flights in 2023 achieved only ~78% on-time
arrival rate — meaning 1 in 5 flights arrived delayed.
Root causes are not systematically identified, measured,
or monitored across the industry.
Problem Statement
DMAIC Timeline
Identify the top 2-3 root causes of US domestic flight
delays using 2023 BTS data, quantify their sigma-level
impact, and design a KPI monitoring dashboard to enable
data-driven operational decisions.
Goal Statement
Scope
CTQ Metrics
Tools & Methodology
IN SCOPE:
• All US domestic flights, full year 2023
• All reporting carriers
• All delay cause categories (carrier, weather, NAS,
security, late aircraft)
OUT OF SCOPE:
• International flights
• Airport ground crew operations
Statistics: Excel (t-test, Regression, Cp/Cpk)
Data Source: BTS On-Time Performance 2023
Owner: Sabab Abrar Hamim
Cert: Lean Six Sigma Green Belt (June 2026)
University: UT Arlington — Industrial, Manufacturing, and Systems Eng.
Minors: Information Systems | Sustainable Eng.
Timeline: June – August 2026
Secondary Metric:
Average Arrival Delay (minutes)
DPMO & Sigma Level